## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project Initiation
Milestone: Kickoff meeting
Gather Stakeholder input |  | 2021-03-01 | 2021-03-02 | 1 | PM | Done
Align and evaluate stakeholders |  | 2021-03-02 | 2021-03-04 | 2 | PM | Done
Gather input from the waitstaff |  | 2021-03-04 | 2021-03-06 | 2 | PM | Done
Finalize Project Charter |  | 2021-03-08 | 2021-03-09 | 1 | PM | Done
Schedule kick off meeting |  | 2021-03-09 | 2021-03-10 | 1 | PM | Done
Sourcing
Milestone: Tablets shipment
Research tablet vendors and options |  | 2021-03-10 | 2021-03-13 | 3 | PM | Done
Generate quotes and review costs |  | 2021-03-15 | 2021-03-17 | 2 | PM | Done
Choose tablet vendor |  | 2021-03-17 | 2021-03-18 | 1 | PM | Done
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 2021-03-18 | 2021-03-20 | 2 | PM | Done
Create SOW for vendor |  | 2021-03-22 | 2021-03-27 | 5 | PM | Done
Finalize purchase agreement |  | 2021-03-29 | 2021-03-30 | 1 | Purchasing | Done
Tablets Shipment |  | 2021-03-30 | 2021-04-13 | 14 | Purchasing | Done
Installation
Milestone: Complete installation, test and troubleshooting
Gather wiring requirement for both restaurants |  | 2021-03-30 | 2021-04-01 | 2 | PM | Done
Schedule electrician for wiring |  | 2021-04-01 | 2021-04-02 | 1 | PM & GM | Done
Create menu and coupon mock up |  | 2021-03-30 | 2021-04-13 | 14 | Head of Marketing | Done
Check our POS system version and compatibility |  | 2021-03-30 | 2021-03-31 | 1 | PM | Done
Inspection on the arrived tablets |  | 2021-04-13 | 2021-04-14 | 1 | Purchasing | Done
Install and setup the tablet at both restaurants |  | 2021-04-14 | 2021-04-15 | 1 | PM & GM | Done
Software Installaion |  | 2021-04-14 | 2021-04-19 | 5 | PM & GM | Done
POS system integration |  | 2021-04-19 | 2021-04-20 | 1 | PM & GM | Done
Upload menu and coupon |  | 2021-04-19 | 2021-04-20 | 1 | PM & GM | Done
Completing installation, test, and troubleshooting |  | 2021-04-19 | 2021-04-20 | 1 | PM & GM | Done
Training
Milestone: Complete Training for all staff at both locations
Review Training material from Vendor |  | 2021-03-30 | 2021-04-06 | 7 | HR | Done
Finalize training material |  | 2021-04-06 | 2021-04-13 | 7 | HR | Done
Training for selected staff by tablet vendor |  | 2021-04-13 | 2021-04-15 | 2 | PM & HR | Done
Training for Manager by tablet vendor |  | 2021-04-15 | 2021-04-17 | 2 | PM & HR | Done
Completing training for Rest of staff at both locations |  | 2021-04-17 | 2021-04-19 | 2 | PM & HR | Done
Launch and evaluation
Milestone: Project Closeout
Run test and simulation on both restaurants |  | 2021-04-19 | 2021-04-20 | 1 | GM | Done
Milestone: Pilot Launch |  | 2021-04-20 | 2021-04-21 | 1 | GM | Done
Implement a post-dining survey to assess customer satisfaction |  | 2021-04-20 | 2021-04-27 | 7 | Head of Marketing | Done
Gather Data points related to dining time, item sales, and incorrect order |  | 2021-04-20 | 2021-05-04 | 14 | PM | Done
Review the gethered data with stakeholders |  | 2021-05-04 | 2021-05-05 | 1 | PM | Done
Milestone: Project Closeout |  | 2021-05-05 | 2021-05-10 | 5 | PM | Done
Formulas:
Due Date = [Start Date]+[Duration]
Start Date = [Duration, row above]+[Start Date, row above]
Start Date = [Start Date, row above]+[Duration, row above]+2

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Project Initiation
Milestone: Kickoff meeting
Gather Stakeholder input |  | 1
Align and evaluate stakeholders |  | 2
Gather input from the waitstaff |  | 2 | 1 | 2 | 3
Finalize Project Charter |  | 1
Schedule kick off meeting |  | 1
Sourcing
Milestone: Tablets shipment
Research tablet vendors and options |  | 3
Generate quotes and review costs |  | 2
Choose tablet vendor |  | 1
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 2 | 1 | 2 | 3
Create SOW for vendor |  | 5 | 3 | 5 | 7
Finalize purchase agreement |  | 1 | 1 | 1 | 2
Tablets Shipment |  | 14 | 10 | 14 | 18
Installation
Milestone: Complete installation, test and troubleshooting
Gather wiring requirement for both restaurants |  | 2 | 1 | 2 | 3
Schedule electrician for wiring |  | 1 | 1 | 1 | 2
Create menu and coupon mock up |  | 14 | 5 | 10 | 14 | L
Check our POS system version and compatibility |  | 1 | 1 | 1 | 2
Inspection on the arrived tablets |  | 1 | 1 | 1 | 2
Install and setup the tablet at both restaurants |  | 1 | 1 | 1 | 2
Software Installaion |  | 5 | 3 | 5 | 7
POS system integration |  | 1 | 1 | 1 | 2
Upload menu and coupon |  | 1 | 1 | 1 | 2
Completing installation, test, and troubleshooting |  | 1 | 1 | 1 | 2
Training
Milestone: Complete Training for all staff at both locations
Review Training material from Vendor |  | 7 | 5 | 7 | 9
Finalize training material |  | 7 | 5 | 7 | 9
Training for selected staff by tablet vendor |  | 2 | 1 | 2 | 2
Training for Manager by tablet vendor |  | 2 | 1 | 2 | 2
Completing training for Rest of staff at both locations |  | 2 | 1 | 2 | 2
Launch and evaluation
Milestone: Project Closeout
Run test and simulation on both restaurants |  | 1 | 1 | 1 | 2
Milestone: Pilot Launch |  | 1 | 1 | 1 | 2
Implement a post-dining survey to assess customer satisfaction |  | 7 | 5 | 7 | 9
Gather Data points related to dining time, item sales, and incorrect order |  | 14 | 10 | 14 | 20
Review the gethered data with stakeholders |  | 1 | 1 | 1 | 2
Milestone: Project Closeout |  | 5 | 3 | 5 | 7

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Best Practices For Using iPads in the Restaurant Industry | https://www.lockncharge.com/eu/blog/industry-news/best-practices-for-using-ipads-in-the-restaurant-industry/
The Top 7 Tablet POS Systems For Restaurants | https://www.merchantmaverick.com/top-tablet-pos-systems-restaurants/

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | average table turn time by 30 minutes | How can we improve? | amount of time | FALSE
Customer satisfaction | checkout time of one minute or less | How can we improve? | amount of time | FALSE
Customer satisfaction | less than 5% of customers who use the tablets to report technical issues each week | Do customers have better dining experience with the tablets? Do all the tablets work as expected? | number of technical issues | FALSE
Customer satisfaction | 98% order accuracy | Do customers receive the correct orders? | number of incorrect orders, level of satisfaction | FALSE
Customer satisfaction | average wait time of ten minutes or less before customers are seated | How much time customers spend waiting to be seated? | wait time, observed behavior | FALSE
Easy of use |  | Do customers easily navigate the tablets? | amount of time to place the order on tablet | FALSE
Design |  | Do customers think the tablets have an attractive design? | number of coupon used and promotion sold | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
|  |  | What age group do you belong to? | Scaled | <20 | >=20 && <40 | >40
|  |  | Did you have visited Sauce & Spoon in the past? | Yes/No | Yes | No
Customer satisfaction - average table turn time by 30 minutes | How can we improve? | amount of time | How long did your dinner take tonight? | Multiple choice | less then 30 min | more than 30 min | more than 1 hour | more than 2 hours
Customer satisfaction - checkout time of one minute or less | How can we improve? | amount of time | How long did you checkout after finishing your meal? | Multiple choice | less than 1 min | less than 2 min | less than 3 min | more than 3 min
Customer satisfaction - less than 5% of customers who use the tablets to report technical issues each week | Do customers have better dining experience with the tablets? Do all the tablets work as expected? | number of technical issues | Did you used tablets during your visit? | Yes/No | Yes | No
| Do customers have better dining experience with the tablets? Do all the tablets work as expected? | number of technical issues | Did you have any technical issue with our tablets? | Yes/No | Yes | No
| Do customers have better dining experience with the tablets? Do all the tablets work as expected? | number of technical issues | What kind of technical issue was that? | Open-ended | Open-ended
Customer satisfaction - 98% order accuracy | Do customers receive the correct orders? | number of incorrect orders, level of satisfaction | Did you receiving the correct order? | Yes/No | Yes | No
Customer satisfaction - average wait time of ten minutes or less before customers are seated | How much time customers spend waiting to be seated? | wait time, observed behavior | How long did you wait before you was seated? | Multiple choice | less than 5 min | less than 10 min | less than 15 min | more than 15 min | more than 20 min
Easy of use | Do customers easily navigate the tablets? | amount of time to place the order on tablet | Did our tablets are easy to navigate? | Yes/No | Yes | No
Design | Do customers think the tablets have an attractive design? | number of coupon used and promotion sold | On a scale of 1-5, 1 being very bad and 5 being excellent, how would you rate our tablet design? | Scaled | 1: Very Bad | 2: Bad | 3: Okay | 4: Good | 5: Excellent
|  |  | Did you have any additional suggetion how we can improve experience with out tablet menu? | Open-ended | Open-ended
|  |  | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience in the Sauce & Spoon? | Scaled | 1: Very dissatisfied | 2: Somewhat dissatisfied | 3: Neither satisfied nor dissatisfied | 4: Somewhat satisfied | 5: Very Satisfied