## Sheet1
ASSOCIATED USER STORY | TASK | ESTIMATED TASK TIME | DATE COMPLETED | SUM
1 | Design wireframe for the application | 6 | 2016-04-11 | 110.75
1 | Setup iOS development environment | 8 | 2016-04-11 | 108.75
24 | Design page layout | 6 | 2016-04-11 | 110.75
24 | Generate wireframe for page layout | 2 | 2016-04-11 | 114.75
24 | Write source code for page layout | 8 | 2016-04-13 | 108.75
24 | Review source code for page layout | 1 | 2016-04-13 | 115.75
24 | Write acceptance criteria for page layout | 0.5 | 2016-04-13 | 116.25
24 | Write acceptance tests for page layout | 0.5 | 2016-04-13 | 116.25
24 | Execute acceptance tests for page layout | 1 | 2016-04-14 | 115.75
24 | Write internal documentation for page layout | 1 | 2016-04-15 | 115.75
25 | Write source code for off-white background | 0.25 | 2016-04-12 | 116.5
25 | Write unit tests for off-white background | 0.25 | 2016-04-12 | 116.5
25 | Review source code for off-white background | 0.25 | 2016-04-13 | 116.5
25 | Write acceptance criteria for off-white background | 0.25 | 2016-04-13 | 116.5
25 | Write acceptance tests for off-white background | 0.25 | 2016-04-13 | 116.5
25 | Execute acceptance tests for off-white background | 0.25 | 2016-04-14 | 116.5
26 | Write acceptance criteria for solo reading | 0.5 | 2016-04-13 | 116.25
26 | Write acceptance tests for solo reading | 0.5 | 2016-04-13 | 116.25
26 | Write source code for solo reading | 3 | 2016-04-14 | 113.75
26 | Review source code for solo reading | 1 | 2016-04-14 | 115.75
26 | Write unit tests for solo reading | 1 | 2016-04-14 | 115.75
26 | Execute acceptance tests for solo reading | 1 | 2016-04-15 | 115.75
26 | Write internal documentation for solo reading | 0.5 | 2016-04-15 | 116.25
26 | Write user manual for solo reading | 0.5 | 2016-04-15 | 116.25
27 | Write source code for portrait and landscape modes | 6 | 2016-04-14 | 110.75
27 | Review source code for portrait and landscape modes | 0.5 | 2016-04-14 | 116.25
27 | Write unit tests for portrait and landscape modes | 1 | 2016-04-14 | 115.75
27 | Write acceptance criteria for portrait and landscape modes | 0.5 | 2016-04-14 | 116.25
27 | Write acceptance tests for portrait and landscape modes | 0.5 | 2016-04-14 | 116.25
27 | Execute acceptance tests for portrait and landscape modes | 0.25 | 2016-04-15 | 116.5
27 | Write internal documentation for portrait and landscape modes | 1 | 2016-04-15 | 115.75
28 | Write source code for pictures in content | 4 | 2016-04-13 | 112.75
28 | Write unit tests for pictures in content | 1 | 2016-04-13 | 115.75
28 | Review source code for pictures in content | 1 | 2016-04-14 | 115.75
28 | Write acceptance criteria for pictures in content | 0.5 | 2016-04-14 | 116.25
28 | Write acceptance tests for pictures in content | 0.5 | 2016-04-14 | 116.25
28 | Execute acceptance tests for pictures in content | 0.5 | 2016-04-14 | 116.25
28 | Write internal documentation for pictures in content | 1 | 2016-04-15 | 115.75
29 | Write source code for adjustable font sizes | 3 | 2016-04-14 | 113.75
29 | Review source code for adjustable font sizes | 1 | 2016-04-14 | 115.75
29 | Write unit tests for adjustable font sizes | 1 | 2016-04-14 | 115.75
29 | Write acceptance criteria for adjustable font sizes | 0.5 | 2016-04-14 | 116.25
29 | Write acceptance tests for adjustable font sizes | 0.5 | 2016-04-14 | 116.25
29 | Execute acceptance tests for adjustable font sizes | 0.5 | 2016-04-15 | 116.25
29 | Write internal documentation for adjustable font sizes | 1 | 2016-04-15 | 115.75
29 | Write user manual for adjustable font sizes | 1 | 2016-04-15 | 115.75
32 | Write source code for connecting with remote user | 16 | 2016-04-13 | 100.75
32 | Review source code for connecting with remote user | 2 | 2016-04-13 | 114.75
32 | Write acceptance criteria for connecting with remote user | 0.5 | 2016-04-13 | 116.25
32 | Write acceptance tests for connecting with remote user | 0.5 | 2016-04-13 | 116.25
32 | Execute acceptance tests for connecting with remote user | 1 | 2016-04-14 | 115.75
32 | Write unit tests for connecting with remote user | 2 | 2016-04-15 | 114.75
32 | Write internal documentation for connecting with remote user | 1 | 2016-04-15 | 115.75
32 | Write user manual for connecting with remote user | 1 | 2016-04-15 | 115.75
33 | Write acceptance criteria for connecting with audio | 0.5 | 2016-04-13 | 116.25
33 | Write acceptance tests for connecting with audio | 0.5 | 2016-04-13 | 116.25
33 | Write source code for connecting with audio | 16 | 2016-04-14 | 100.75
33 | Review source code for connecting with audio | 1 | 2016-04-15 | 115.75
33 | Write unit tests for connecting with audio | 2 | 2016-04-15 | 114.75
33 | Execute acceptance tests for connecting with audio | 0.5 | 2016-04-15 | 116.25
33 | Write internal documentation for connecting with audio | 1 | 2016-04-15 | 115.75
33 | Write user manual for connecting with audio | 1 | 2016-04-15 | 115.75
116.75

## Pivot Table 1
Remaining Hours
94.75
94.25
57.5
17.25
0

## Sheet3
DATE COMPLETED | SUM of ESTIMATED TASK TIME | Remaining Hours | Prediction
2016-04-10 | 0 | 116.75 | 116.75
2016-04-11 | 22 | 94.75 | 93.4
2016-04-12 | 0.5 | 94.25 | 70.05
2016-04-13 | 36.75 | 57.5 | 46.7
2016-04-14 | 40.25 | 17.25 | 23.35
2016-04-15 | 17.25 | 0 | 0
Grand Total | 116.75