## Sheet1
US ID# | USER STORY | TASKS | HOUR ESTIMATE | ASSIGNED TO
2 | As a reader, I want the application to remotely access the book content, so that the application doesn't require a large amount of memory | Write source code for pulling material from database | 10 | Josh
|  | Review source code for pulling material from database | 2
|  | Write unit tests for pulling material from database | 6 | Josh
|  | Write acceptance criteria for pulling material from database | 1
|  | Write acceptance tests for pulling material from database | 1
|  | Execute acceptance tests for pulling material from database | 1 | You
|  | Write internal documentation for pulling material from database | 2 | Josh
3 | As a reader, I want to be able to save selected reading material locally to the device, so that I can read without a wireless connection | Determine how a user saves material locally | 2 | Kat
|  | Write source code for saving material locally | 10 | Kat
|  | Review source code for saving material locally | 1
|  | Write unit tests for saving material locally | 4 | Kat
|  | Write acceptance criteria for for saving material locally | 0.5
|  | Write acceptance tests for saving material locally | 0.5
|  | Execute acceptance tests for saving material locally | 1 | You
|  | Write internal documentation for saving material locally | 1 | Kat
|  | Write user manual for saving material locally | 1 | Kat
4 | As a reader, I want to be able to browse all available reading material, so that I can choose something to read | Design ability to browse reading material | 1 | Alexa
|  | Write source code for browsing reading material | 6 | Alexa
|  | Review source code for browsing reading material | 1
|  | Write unit tests for browsing reading material | 3 | Alexa
|  | Write acceptance criteria for browsing reading material | 0.5
|  | Write acceptance tests for browsing reading material | 0.5
|  | Execute acceptance tests for browsing reading material | 0.5 | You
|  | Write internal documentation for browsing reading material | 0.5 | Alexa
|  | Write user manual for browsing reading material | 0.5 | Alexa
5 | As a reader, I want to see the covers of the books while I'm browsing through them, so that I can judge a book by its cover | Write source code for seeing book covers while browsing | 5 | Alexa
|  | Review source code for seeing book covers while browsing | 1
|  | Write unit tests for seeing book covers while browsing | 2 | Alexa
|  | Write acceptance criteria for seeing book covers while browsing | 0.5
|  | Write acceptance tests for seeing book covers while browsing | 0.5
|  | Execute acceptance tests for seeing book covers while browsing | 0.5 | You
|  | Write internal documentation for seeing book covers while browsing | 1 | Alexa
6 | As a reader, I want to select reading material, so that I can read it | Write source code for selecting reading material | 4
|  | Review source code for selecting reading material | 1
|  | Write unit tests for selecting reading material | 2
|  | Write acceptance criteria for selecting reading material | 0.5
|  | Write acceptance tests for selecting reading material | 0.5
|  | Execute acceptance tests for selecting reading material | 0.5 | You
|  | Write internal documentation for selecting reading material | 1
|  | Write user manual for selecting reading material | 1
7 | As a reader, I want to be able to sort reading material based on comprehension difficulty or genre | Determine how a user sorts reading material | 1
|  | Write source code for sorting reading material | 4
|  | Review source code for sorting reading material | 1
|  | Write unit tests for sorting reading material | 2
|  | Write acceptance criteria for sorting reading material | 0.5
|  | Write acceptance tests for sorting reading material | 0.5
|  | Execute acceptance tests for sorting reading material | 1 | You
|  | Write internal documentation for sorting reading material | 1
|  | Write user manual for sorting reading material | 1
8 | As a reader, I want to be able to search for reading material, so that I can find a specific piece of reading material that I have in mind | Design search feature | 2
|  | Write source code for searching for reading material | 6
|  | Review source code for searching for reading material | 1
|  | Write unit tests for searching for reading material | 4
|  | Write acceptance criteria for searching for reading material | 0.5
|  | Write acceptance tests for searching for reading material | 0.5
|  | Execute acceptance tests for searching for reading material | 1 | You
|  | Write internal documentation for searching for reading material | 1
|  | Write user manual for searching for reading material | 1
40 | As a reader, I want my place in a book to be saved, so that I can return to that place at a later time | Determine how a user saves their place | 2
|  | Write source code for book marking | 6
|  | Review source code for book marking | 1
|  | Write unit tests for book marking | 4
|  | Write acceptance criteria for book marking | 0.5
|  | Write acceptance tests for book marking | 0.5
|  | Execute acceptance tests for book marking | 0.5 | You
|  | Write internal documentation for book marking | 1
|  | Write user manual for book marking | 1
|  | TOTAL HOURS | 124
|  |  | DEVELOPER | AVAILABLE HOURS | ASSIGNED HOURS
|  |  | Alexa | 35 | 19
|  |  | Josh | 40 | 18
|  |  | Kat | 30 | 18
|  |  | Your Tasks | - | 6