## Sheet1
US ID# | USER STORY | TASKS | HOUR ESTIMATE | ASSIGNED TO
10 | As a reader, I want to be able to create an account, so that I can save information about my activity for my reference later | Determine how a user creates an account | 2 | Kat/Daniel
|  | Write source code for creating an account | 4 | Kat
|  | Review source code for creating an account | 1
|  | Write unit tests for creating an account | 2 | Kat
|  | Write acceptance criteria for creating an account | 0.5
|  | Write acceptance tests for creating an account | 0.5
|  | Execute acceptance tests for creating an account | 0.5 | You
|  | Write internal documentation for creating an account | 1 | Kat
|  | Write user manual for creating an account | 1 | Kat
11 | As an account holder, I want to be able to log into my account, so that I can access my account | Write source code for logging into an account | 2 | Kat
|  | Review source code for logging into an account | 0.5
|  | Write unit tests for logging into an account | 2 | Kat
|  | Write acceptance criteria for logging into an account | 0.5
|  | Write acceptance tests for logging into an account | 0.5
|  | Execute acceptance tests for logging into an account | 0.5 | You
|  | Write internal documentation for logging into an account | 0.5 | Kat
|  | Write user manual for logging into an account | 0.5 | Kat
14 | As an account holder, I want to be able to add reading material to my To-Read list, so that I can read it later | Write source code for adding material to the to-read list | 5 | Alexa
|  | Review source code for adding material to the to-read list | 1
|  | Write unit tests for adding material to the to-read list | 3 | Alexa
|  | Write acceptance criteria for adding material to the to-read list | 0.5
|  | Write acceptance tests for adding material to the to-read list | 0.5
|  | Execute acceptance tests for adding material to the to-read list | 0.5 | You
|  | Write internal documentation for adding material to the to-read list | 1 | Alexa
|  | Write user manual for adding material to the to-read list | 1 | Alexa
15 | As an account holder, I want to be able to delete reading material from my To-Read list, so that it is no longer found on the list | Write source code for deleting material to the to-read list | 1 | Alexa
|  | Review source code for deleting material to the to-read list | 0.5
|  | Write unit tests for deleting material to the to-read list | 1 | Alexa
|  | Write acceptance criteria for deleting material to the to-read list | 0.5
|  | Write acceptance tests for deleting material to the to-read list | 0.5
|  | Execute acceptance tests for deleting material to the to-read list | 0.5 | You
|  | Write internal documentation for deleting material to the to-read list | 0.5 | Alexa
|  | Write user manual for deleting material to the to-read list | 0.5 | Alexa
16 | As an account holder, I want to be able to add reading material to my Favorites list, so that I have all my favorite reading material in one place | Write source code for adding material to the favorites list | 5 | Alexa
|  | Review source code for adding material to the favorites list | 1
|  | Write unit tests for adding material to the favorites list | 3 | Alexa
|  | Write acceptance criteria for adding material to the favorites list | 0.5
|  | Write acceptance tests for adding material to the favorites list | 0.5
|  | Execute acceptance tests for adding material to the favorites list | 0.5 | You
|  | Write internal documentation for adding material to the favorites list | 1 | Alexa
|  | Write user manual for adding material to the favorites list | 1 | Alexa
17 | As an account holder, I want to be able to delete reading material to my Favorites list, so that it is no longer found on the list | Write source code for deleting material to the favorites list | 1 | Alexa
|  | Review source code for deleting material to the favorites list | 0.5
|  | Write unit tests for deleting material to the favorites list | 1 | Alexa
|  | Write acceptance criteria for deleting material to the favorites list | 0.5
|  | Write acceptance tests for deleting material to the favorites list | 0.5
|  | Execute acceptance tests for deleting material to the favorites list | 0.5 | You
|  | Write internal documentation for deleting material to the favorites list | 0.5 | Alexa
|  | Write user manual for deleting material to the favorites list | 0.5 | Alexa
20 | As an account holder, I want to have my reading fluency and reading comprehension level tested, so that I can use it to identify appropriate reading material | Design comprehension testing | 3 | Josh/Daniel
|  | Write source code for comprehension testing | 5 | Josh
|  | Review source code for comprehension testing | 1
|  | Write unit tests for searching for comprehension testing | 3 | Josh
|  | Write acceptance criteria for comprehension testing | 0.5
|  | Write acceptance tests for comprehension testing | 0.5
|  | Execute acceptance tests for comprehension testing | 0.5 | You
|  | Write internal documentation for comprehension testing | 1 | Josh
|  | Write user manual for comprehension testing | 1 | Josh
22 | As an account holder, I want the application to track my reading fluency and comprehension improvements, so that I can have material updated to my appropriate skill level | Determine how improvements will be tracked | 3
|  | Write source code for tracking reading improvements | 6
|  | Review source code for tracking reading improvements | 1
|  | Write unit tests for tracking reading improvements | 2
|  | Write acceptance criteria for tracking reading improvements | 0.5
|  | Write acceptance tests for tracking reading improvements | 0.5
|  | Execute acceptance tests for tracking reading improvements | 0.5 | You
|  | Write internal documentation for tracking reading improvements | 1
|  | Write user manual for tracking reading improvements | 1
31 | As a reader, I want to select unknown words to see their definition, so that I can learn the definition and pronunciation of new words | Determine how the definition tool works | 3
|  | Write source code for defining words | 7
|  | Review source code for defining words | 2
|  | Write unit tests for defining words | 3
|  | Write acceptance criteria for defining words | 0.5
|  | Write acceptance tests for defining words | 0.5
|  | Execute acceptance tests for defining words | 0.5 | You
|  | Write internal documentation for defining words | 1
|  | Write user manual for defining words | 1
38 | As a reader, I want to be be matched with a remote reader based on reading level, so that we both enjoy our time and feel equally challenged when reading together | Write source code for reading level matches | 5
|  | Review source code for reading level matches | 1
|  | Write unit tests for reading level matches | 2
|  | Write acceptance criteria for reading level matches | 0.5
|  | Write acceptance tests for reading level matches | 0.5
|  | Execute acceptance tests for reading level matches | 1 | You
|  | Write internal documentation for reading level matches | 1
|  | Write user manual for reading level matches | 1
|  | TOTAL HOURS | 116
|  |  | DEVELOPER | AVAILABLE HOURS | ASSIGNED HOURS
|  |  | Alexa | 40 | 26
|  |  | Josh | 40 | 13
|  |  | Kat | 35 | 15
|  |  | Your Tasks | - | 5.5